## Features
# | Feature | Description | Status | Week
1 | Multi-tenant foundation | Each contractor gets an isolated workspace; data never crosses tenants | Done | 1
2 | Auth (Clerk) | Sign up / sign in, session management | Done | 1
3 | Onboarding wizard | New contractor picks a slug -> workspace auto-provisioned | Done | 1
4 | BrandKit | Logo, colors, brand voice, bio, license/insurance shown in widget | Done | 2
5 | Homeowner widget | Embeddable page where homeowners upload photos & chat | Done | 2
6 | AI photo renders (FLUX/Fal.ai) | Upload kitchen photo -> AI shows renovated version in ~60s | Done | 2
7 | AI chat assistant (Claude) | 24/7 assistant answering using contractor's own info | Done | 3
8 | Real dashboard stats | Live lead/render counts on dashboard home | Done | 3
9 | Embed snippet generator | Copy-paste iframe code for contractor's site | Done | 3
10 | Tenant provisioning API | Automated workspace creation on signup | Done | 4
11 | Stripe billing | Checkout, customer portal, plan upgrades via webhook | Done | 4
12 | Follow-up emails | Automatic reminder emails to leads who go quiet | Done | 4
13 | Security hardening pass #1 | Rate limiting, validation, error boundaries, admin panel, theming | Done | 5
14 | Plan limits + usage metering | Starter/Growth/Pro render & lead caps enforced server-side | Done | 6
15 | GoHighLevel CRM sync | Leads pushed to contractor's GHL pipeline | Done | 6
16 | AI memory / RAG (pgvector) | Contractor uploads docs/FAQs; chatbot retrieves relevant chunks | Done | 6.5
17 | SEO module | AI-generated local landing pages with JSON-LD schema | Done | 6.5
18 | GHL OAuth connect flow | One-click CRM connection (no manual API keys) | Done | 7
19 | Trial reminder emails | "Your trial ends in N days" automated emails | Done | 7
20 | Chat trimming + usage banner | Keeps token costs bounded; shows usage in dashboard | Done | 7
21 | AI Scope Analyzer | Turns chat into structured project spec | Done | 8
22 | AI Budget Estimator | Price range using contractor's own pricing rules | Done | 8
23 | AI Proposal Generator | One-click web proposal, e-signature, Stripe deposit | Done | 9
24 | Review & Testimonial Assistant | 4-5 star -> public review links; 1-3 star -> private alert + AI draft reply | Done | 10
25 | Tamper-evident audit log | Every signature/payment/settings/integration change logged with IP + actor | Done | 10.5
26 | Email XSS hardening | User text escaped before going into HTML emails | Done | 10.5
27 | Public API rate limiting | /api/v1/leads and /api/v1/renders capped per-IP | Done | 10.5
28 | Public API key auth | /api/v1/* requires per-tenant Bearer key, managed in Settings | Done | 10.6
29 | Render lookup tenant scoping | GET /api/v1/renders?id= requires owning tenant's API key | Done | 10.6

## Test Proof
Check | Result | Notes
npm run typecheck (tsc --noEmit) | PASS | 0 errors
npm run lint (eslint) | PASS | 0 errors, 0 warnings
npm run build (next build, production) | PASS | All ~45 routes compiled successfully
drizzle-kit generate (schema -> migration) | PASS | Migration 0001_shallow_vivisector.sql generated
Manual end-to-end funnel checklist (see docs/PROJECT_STATUS.md section 2.3)
| To run on a configured environment | Sign up -> onboarding -> workspace created
| To run on a configured environment | BrandKit configured (logo, colors, voice)
| To run on a configured environment | Embed widget loads at /embed/<slug>
| To run on a configured environment | Photo upload + AI render completes
| To run on a configured environment | Chat assistant responds using BrandKit voice + RAG
| To run on a configured environment | Lead captured in dashboard
| To run on a configured environment | Follow-up email sent (Resend)
| To run on a configured environment | Scope -> Estimate -> Proposal -> Send
| To run on a configured environment | Proposal signed (e-sign) + Stripe deposit paid
| To run on a configured environment | Review request: 5-star -> public links, 2-star -> private owner alert
| To run on a configured environment | API key created in Settings; /api/v1/leads call with Bearer key returns 201
| To run on a configured environment | /api/v1/leads call WITHOUT Bearer key returns 401 (auth enforced)

## Security
Control | Detail | Status
Tenant isolation | Every query scoped by tenantId via requireTenant() | Implemented
Input validation | Zod schemas on every API route | Implemented
Stripe webhook verification | stripe.webhooks.constructEvent signature check | Implemented
CRM credential encryption | AES-256-GCM at rest (ENCRYPTION_KEY) | Implemented
Photo privacy | EXIF stripped on upload | Implemented
Rate limiting | Per-IP limits on all public endpoints | Implemented
Unguessable tokens | Proposal & review links use random access tokens | Implemented
SEO HTML safety | AI output rendered via escaped structured templates, never raw HTML | Implemented
Audit logging | audit_log table: signatures, payments, settings, integrations, API keys | Implemented
Email XSS protection | escapeHtml() on all user-controlled email fields | Implemented
Public API authentication | /api/v1/* requires hashed per-tenant Bearer key | Implemented
Render lookup scoping | GET /api/v1/renders?id= scoped to API-key tenant | Implemented
Distributed rate limiting | Move in-process limiter to Upstash Redis for multi-region | Recommended
Structured log export | Ship audit_log to Axiom/BetterStack | Recommended
CSP headers on widget | Content-Security-Policy for embed surface | Recommended
Penetration test | Before Agency/white-label tier launch | Recommended

## Roadmap
Week/Month | Theme | Deliverables | Status
11 | Multi-CRM hub | HubSpot + Jobber adapters, field-mapping UI, sync dead-letter view | Not started
12 | Lead intelligence | AI lead scoring (0-100), hot-lead SMS routing, scoring feedback loop | Not started
13 | Launch polish | sitemap.xml/robots.txt, Playwright funnel test, public launch checklist | Not started
M4 | SAM2 region-select rendering | Tap-to-select regions, ControlNet depth/edge conditioning | Not started
M5 | Voice + speed-to-lead | Vapi/Bland AI voice agent, SMS follow-up channel | Not started
M6 | Agency / white-label tier | Sub-accounts, white-label theming, GHL Snapshot listing | Not started
M7 | Vertical: bathroom remodeling | New vertical_config, style references, prompt templates | Not started
M8 | Custom LoRA + ROI dashboard | Per-tenant style training, revenue-impact dashboard | Not started
M9 | Vertical: landscaping | Same pattern as bathroom, new style set | Not started

## Monetization
Lever | Detail | Why it matters
Tiered metering | Starter/Growth/Pro/Agency caps on renders & leads | Already enforced
Annual plans | 2 months free for annual commitment | Improves cashflow & churn
Setup fee | $497-$997 one-time white-glove onboarding | Pure margin
Add-ons | SEO page packs, custom LoRA + maintenance, AI voice agent | ARPU expansion
Agency / white-label tier | 1 sale = 10+ contractor sub-accounts | Highest leverage channel
Referral program | 30% rev-share, contractor refers contractor | Low-CAC growth
API access add-on | Now authenticated -- sell as Pro+/Agency perk (Zapier, etc.) | New, enabled this session